## Slide 1: Project Initiation & Planning
Duration 1 week
Dependencies: None
Status: Not Started
Resources: Project Manager

## Slide 2: Requirements Gathering & Analysis
Duration 2 weeks
Dependencies: Project Initiation & Planning
Status: Not Started
Resources: Project Manager, Development Team

## Slide 3: System Architecture Design
Duration 2 weeks
Dependencies: Requirements Gathering & Analysis
Status: Not Started
Resources: Development Team

## Slide 4: UI/UX Design
Duration 3 weeks
Dependencies: System Architecture Design
Status: Not Started
Resources: UI/UX Designer

## Slide 5: Backend Development
Duration 12 weeks
Dependencies: System Architecture Design
Status: Not Started
Resources: Development Team

## Slide 6: iOS App Development
Duration 10 weeks
Dependencies: UI/UX Design, Backend Development
Status: Not Started
Resources: iOS Development Team

## Slide 7: Android App Development
Duration 10 weeks
Dependencies: UI/UX Design, Backend Development
Status: Not Started
Resources: Android Development Team

## Slide 8: Payment Gateway Integration
Duration 4 weeks
Dependencies: Backend Development
Status: Not Started
Resources: Development Team

## Slide 9: Quality Assurance & Testing
Duration 6 weeks
Dependencies: iOS App Development, Android App Development, Payment Gateway Integration
Status: Not Started
Resources: QA Team

## Slide 10: User Documentation & Onboarding Guides
Duration 2 weeks
Dependencies: Quality Assurance & Testing
Status: Not Started
Resources: Technical Writer

## Slide 11: Deployment of Backend
Duration 1 week
Dependencies: Quality Assurance & Testing
Status: Not Started
Resources: DevOps Team

## Slide 12: App Store Submission (iOS & Android)
Duration 1 week
Dependencies: Quality Assurance & Testing, Deployment of Backend
Status: Not Started
Resources: Project Manager

## Slide 13: Marketing & Launch Preparation
Duration 4 weeks
Dependencies: User Documentation & Onboarding Guides, Deployment of Backend, App Store Submission (iOS & Android)
Status: Not Started
Resources: Marketing Team

## Slide 14: Project Launch
Duration 1 day
Dependencies: Marketing & Launch Preparation
Status: Not Started
Resources: Project Manager, Marketing Team

## Slide 15: Post-Launch Monitoring & Bug Fixes
Duration Ongoing
Dependencies: Project Launch
Status: Not Started
Resources: Development Team, QA Team