## Sheet
Task Name | Duration | Dependencies | Status | Resources
--- | --- | --- | --- | ---
Project Initiation & Planning | 1 week | None | Not Started | Project Manager
Requirements Gathering & Analysis | 2 weeks | Project Initiation & Planning | Not Started | Project Manager, Development Team
System Architecture Design | 2 weeks | Requirements Gathering & Analysis | Not Started | Development Team
UI/UX Design | 3 weeks | System Architecture Design | Not Started | UI/UX Designer
Backend Development | 12 weeks | System Architecture Design | Not Started | Development Team
iOS App Development | 10 weeks | UI/UX Design, Backend Development | Not Started | iOS Development Team
Android App Development | 10 weeks | UI/UX Design, Backend Development | Not Started | Android Development Team
Payment Gateway Integration | 4 weeks | Backend Development | Not Started | Development Team
Quality Assurance & Testing | 6 weeks | iOS App Development, Android App Development, Payment Gateway Integration | Not Started | QA Team
User Documentation & Onboarding Guides | 2 weeks | Quality Assurance & Testing | Not Started | Technical Writer
Deployment of Backend | 1 week | Quality Assurance & Testing | Not Started | DevOps Team
App Store Submission (iOS & Android) | 1 week | Quality Assurance & Testing, Deployment of Backend | Not Started | Project Manager
Marketing & Launch Preparation | 4 weeks | User Documentation & Onboarding Guides, Deployment of Backend, App Store Submission (iOS & Android) | Not Started | Marketing Team
Project Launch | 1 day | Marketing & Launch Preparation | Not Started | Project Manager, Marketing Team
Post-Launch Monitoring & Bug Fixes | Ongoing | Project Launch | Not Started | Development Team, QA Team