## Slide 1: Project Kick-off & Planning
Duration 5 days
Dependencies: None
Status: Not Started
Resources: Project Manager, Project Sponsor

## Slide 2: Requirements Gathering & Analysis
Duration 10 days
Dependencies: Project Kick-off & Planning
Status: Not Started
Resources: Project Manager, Development Team

## Slide 3: UI/UX Design
Duration 20 days
Dependencies: Requirements Gathering & Analysis
Status: Not Started
Resources: UI/UX Designers

## Slide 4: Backend Development
Duration 60 days
Dependencies: UI/UX Design
Status: Not Started
Resources: Development Team

## Slide 5: Mobile App Development (iOS)
Duration 50 days
Dependencies: UI/UX Design
Status: Not Started
Resources: Development Team

## Slide 6: Mobile App Development (Android)
Duration 50 days
Dependencies: UI/UX Design
Status: Not Started
Resources: Development Team

## Slide 7: Payment Gateway Integration
Duration 20 days
Dependencies: Backend Development
Status: Not Started
Resources: Development Team

## Slide 8: Testing and Quality Assurance
Duration 30 days
Dependencies: Backend Development, Mobile App Development (iOS), Mobile App Development (Android), Payment Gateway Integration
Status: Not Started
Resources: QA Testers

## Slide 9: User Documentation Creation
Duration 15 days
Dependencies: Testing and Quality Assurance
Status: Not Started
Resources: Technical Writer

## Slide 10: Deployment Planning
Duration 10 days
Dependencies: Testing and Quality Assurance
Status: Not Started
Resources: Project Manager, Development Team

## Slide 11: Marketing Launch Plan
Duration 20 days
Dependencies: Project Kick-off & Planning
Status: Not Started
Resources: Marketing Team

## Slide 12: Pre-Launch Marketing Activities
Duration 30 days
Dependencies: Marketing Launch Plan
Status: Not Started
Resources: Marketing Team

## Slide 13: Application Launch
Duration 1 day
Dependencies: Deployment Planning, Pre-Launch Marketing Activities
Status: Not Started
Resources: Project Manager, Development Team

## Slide 14: Post-Launch Monitoring & Support
Duration Ongoing
Dependencies: Application Launch
Status: Not Started
Resources: Project Manager, Support Team