## Sheet
Task Name | Duration | Dependencies | Status | Resources
--- | --- | --- | --- | ---
Project Initiation | 5 days | None | Not Started | Project Manager, Project Sponsor
Detailed Requirements Gathering | 10 days | Project Initiation | Not Started | Project Manager, Development Team
Database Design | 10 days | Detailed Requirements Gathering | Not Started | Development Team
API Development | 45 days | Database Design | Not Started | Development Team
iOS App Development | 90 days | API Development | Not Started | Development Team
Android App Development | 90 days | API Development | Not Started | Development Team
Payment Gateway Integration | 20 days | API Development | Not Started | Development Team
Testing and Quality Assurance | 30 days | iOS App Development, Android App Development, Payment Gateway Integration | Not Started | Development Team
User Guide and Help Documentation | 15 days | Testing and Quality Assurance | Not Started | Project Manager
Deployment and Release Planning | 10 days | Testing and Quality Assurance | Not Started | Project Manager, Development Team
App Store Submission | 5 days | Deployment and Release Planning | Not Started | Project Manager
Marketing and Launch | 30 days | App Store Submission | Not Started | Marketing Team, Project Manager
Post-Launch Monitoring & Support | Ongoing | Marketing and Launch | Not Started | Development Team, Project Manager